## Slide 1
Atlantic Canada · Startup support events
Staff cannot see who is running what — so events collide
Best problem to solve → Pre-Publish Week List (2-week pilot ≤ CAD 200)
The problem
• About 25 orgs run founder events with no shared view
• Staff publish blind → same-day clashes
• Founders skip, split, or land in the wrong room
• Thin teams cannot take on a daily checklist
The bet
• Shared week list for 5–8 orgs (not all 25)
• Fields: title · date · time band · org
• Check before publish (~2 minutes)
• Measure 2 weeks · stop if unused
Atlantic Canada · Startup event visibility
1 / 6

## Slide 2
What we heard — problems from interviews
Jordan
Publish without knowing peers; rejects daily checklists; thin overlap sample
No shared visibility; cannot add heavy process
Renée
Discovery ≤ CAD 200; needs clash/attendance proof before ongoing spend
Tight budget; proof required; no big build yet
Devon
Eventbrite + 2 Google calendars; no cross-org feed; no prod credentials
Manual sprawl; cannot sustain fragile integrations
Mia
Checks 3 calendars by hand; texts 2 contacts; others found too late
Manual checks fail; incomplete peer network
Sam
Skips/splits when similar events share a day; Thursdays feel packed
Founder harm: missed learning; fragmented attendance
Atlantic Canada · Startup event visibility
2 / 6

## Slide 3
Best problem to solve (framework pick)
Chosen problem: Org staff lack a shared pre-publish view of peer events, so preventable same-day clashes keep happening — and any fix must stay light enough for thin teams.
Why this one
• Matches Jordan’s job and Mia’s workflow pain
• Explains Sam’s skipped / split attendance
• Fits Renée’s proof-before-pay stance
• Respects Devon’s no-fragile-tools limit
• Problem stated without assuming software
Rejected alternatives
• Full event marketplace — too big for CAD 200
• Personal founder budget calendar — wrong customer (Sam)
• Daily coordination checklist — Jordan already rejects
• Production integration next week — not approved
Atlantic Canada · Startup event visibility
3 / 6

## Slide 4
Solution: Pre-Publish Week List
What it is
• One shared sheet for 5–8 orgs
• Fields: title · date · time band · org
• Rule: check → publish → add row (~2 min)
• Run 2 weeks · count clashes · stop if unused
What it is not
• Not an Eventbrite replacement
• Not a public founder app
• Not a paid platform in bet 1
• Not a daily checklist
Success / fail
Success: clashes among pilots drop a lot and posting stays easy. Fail/stop: people ignore the sheet, effort rises, or clashes do not move. Cost envelope ≤ CAD 200 (target $0).
Atlantic Canada · Startup event visibility
4 / 6

## Slide 5
Problem-solving steps 02–06
02 Motivations
Renée: free test, pay later with proof. Jordan: fewer clashes, no heavy work. Devon: sheet only.
03 Mindset
Jordan early majority — short test. Renée & Devon late majority — familiar, low-risk tools only.
04 Gap
Jordan high importance / low satisfaction. Misalignment → only a tiny bet until scores confirmed.
05 Risk
Value first (are clashes real?). Usability next (will they post?). Feasibility easy (sheet).
06 Experiment
2-week sprint: problem → assumption → expected → actual. Stop is a valid success.
Atlantic Canada · Startup event visibility
5 / 6

## Slide 6
Feasible and usable — why this can work
Feasible
• Build time: hours, not months
• Skills present: Devon already runs Google tools
• Budget: within CAD 200; often $0
• No production servers or API credentials
• Start with Harbour Launch + Mia’s peers
Usable
• One ritual: look before publish
• Under ~2 minutes — no daily checklist
• Familiar Sheet for late-majority buyers
• Mia’s 3-calendar scan becomes one list
• If unused → stop; no forced change
Ask
Approve a 2-week Pre-Publish Week List pilot with 5–8 orgs. Measure clashes. Continue, pivot, or stop on Day 15.
Atlantic Canada · Startup event visibility
6 / 6